## Cover_Signoff
Business UAT Sign-off — v2.2 Platform Freeze
Field | Value
Release tag | v2.2-platform-freeze
Deployment commit | 1dff864
Executable baseline | 238bd2f
Recovery anchor | a75bb1e (v2.1.0-jobid-remediation)
IIS rule | Deploy the tag only. Do not deploy Jul head 933445a.
Engineering UAT | CERTIFIED (docs/UAT_READINESS_v2.2_PLATFORM_FREEZE.md)
Schema change | None
Client / SPOC sign-off (complete after live UAT on production IIS)
Role | Name | Date | Signature / initials
Client SPOC
Operations lead
ATS deployment engineer
Overall verdict
PASS / FAIL / CONDITIONAL
Smoke JOBID used
Production URL
Instructions
1) Complete Module_Tracker (one row per product area). 2) Execute Detailed_Cases; record Pass/Fail, screenshot filename, SPOC, date. 3) Do not start CR-001 Phase B, QR, GPS, PWA, or tenancy during this sign-off. 4) Production defects go to docs/R0_HYPERCARE_ISSUE_REGISTER.md (HC-nnn), then a new CR from 238bd2f after hypercare. 5) Reuse certified UAT IDs. Do not invent parallel numbering for unchanged predicates.

## Module_Tracker
Module | In scope | Status | Pass/Fail | Screenshot | SPOC | Date | Notes / HC-ID
Login | login.aspx → homepage_v2.aspx; session USERID + WORKMAN
Create | create_jobid_v2; ARC eligible for IN immediately (UAT-006)
IN | job_inpunch_v2 inbox; no MasterStatusCode=3 gate (UAT-006 / 021)
Permit | job_permitupload_v2; Active + Entry; multi-file (UAT-014 / 015)
OUT | job_outpunch_v2; last OUT confirmation (UAT-029)
Close & Send | btn_FinalizeShift on OUT only; Out-Punch Done / 4 / Exit (UAT-040)
Approval | Out-Punch Done AND EntryExit=Exit (M5 / UAT-035B)
JOB360 | Admin cockpit; raw inbound jobid; encoded V2 hops (UAT-046–049)
Wizard | supervisor_wizard Phase A shell; derived progress; no JOB writes
Mobile | JOB360 Phase E: sticky search/actions, 44px, stacked admin cards

## Detailed_Cases
Case ID | Module | Certified UAT IDs | Business scenario | Expected result | Pass/Fail | Screenshot filename | SPOC | Date | Notes / HC-ID
BUAT-01 | Login | — | Supervisor logs in with valid credentials | homepage_v2 loads; session established
BUAT-02 | Create | UAT-006, UAT-010/011/012 | Create permit-required (ARC) JOBID | JOB created; billing/natures persist; IN inbox lists it immediately
BUAT-03 | Create | UAT-006 skip-permit path | Create skip-permit / non-ARC JOBID | Same as today; IN still available; permit not required before IN
BUAT-04 | IN | UAT-006, UAT-021 | IN-Punch at least one worker on the new JOB | Entry recorded; duplicate Entry still blocked; no code-3 gate
BUAT-05 | Permit | UAT-013, UAT-014, UAT-018, UAT-019 | Upload first permit; leave page; return | JOB still in permit inbox (Active + Entry); FinalUpldStatus Yes
BUAT-06 | Permit | UAT-015, UAT-015A | Upload a second permit file | FileCount increases; JOB remains available
BUAT-07 | OUT | UAT-029 | OUT-Punch workers until last open Entry | Last OUT shows Close & Send confirmation on job_outpunch_v2
BUAT-08 | Close & Send | UAT-040, UAT-040A, UAT-040B | Confirm Close & Send once; retry/refresh | Writes Out-Punch Done / 4 / Exit; second click does not double-write
BUAT-09 | Approval | UAT-035B, M5 | Open Site In-Charge approval list | Closed JOB appears (Out-Punch Done AND Exit)
BUAT-10 | Hub KPIs | UAT-004, UAT-005, UAT-035, UAT-035A | Refresh jobs_and_manpower_v2 after close and after first permit | Pending IN=Created; Pending Permit=Entry+FinalUpldStatus=No; Pending OUT drops after close
BUAT-11 | JOB360 | UAT-046, UAT-047, UAT-048 | Admin searches raw JOBID; hops to Permit / IN / OUT | Cockpit loads; V2 pages decode encoded hops; same JOBID
BUAT-12 | JOB360 | UAT-049, CR001-UAT-010 | Invalid encoded V2 jobid; 360 inbound remains raw | V2 fails closed; 360 does not Base64-decode inbound jobid
BUAT-13 | JOB360 Admin | CR009-UAT-030–035 | Non-admin posts Force OUT / Delete / Cancel; admin uses Inspector | Non-admin rejected; admin Inspector/Edit Core/timeline work; Close still not on 360
BUAT-14 | Mobile | CR009-UAT-036–040 | Open JOB360 on a phone (≤768px) | Scrollable tabs, sticky search/actions, 44px targets, stacked admin cards
BUAT-15 | Wizard | CR001-UAT-001–004, 011, 023 | Open supervisor_wizard; Previous/Next; Open Step | Six stages; chrome only; no admin buttons; Previous does not roll JOB state
BUAT-16 | Wizard | CR001-UAT-005–009, 013–018 | Wizard Open Step to Create/IN/Permit/OUT/Close | Lands on existing V2 URLs; EncodeJobID on hops; Close still on OUT
BUAT-17 | Permit-before-IN | UAT-006, CR001-UAT-006 | Attempt IN on permit-required JOB before any permit file | IN allowed; permit remains optional after IN
BUAT-18 | Permit after close | UAT-015B | After Close & Send, open permit inbox | Closed JOB (Exit) is not in permit inbox

## Hypercare_Log
ID | Date | Reporter | Module | Severity | Summary | Expected vs actual | Repro JOBID | Action | Status | Future CR
HC-001 |  |  | JOB360 | Medium | EXAMPLE — replace or delete |  |  | Future CR | Open
HC-002 |  |  | Wizard | Low | EXAMPLE — replace or delete |  |  | Future CR | Open